MEDCORE – HOSPITAL WARD MANAGEMENT SYSTEM

Team Roles & Task Distribution

# 1. Purpose

This document formalizes the team's task distribution for the Medcore hospital-ward management project (Next.js/TypeScript frontend, Java 21 Spring Boot API, PostgreSQL). It assigns each of the 10 team members to a role, ties that role to the actual repository structure, and lists the diagrams and documentation the team still owes before the deadline.

# 2. Team & Roles (10 people)

| Name | Role | Responsibility |
| --- | --- | --- |
| Ani | Team Leader | Overall lead for the team; represents the project, makes final calls on scope conflicts, and coordinates the defense/demo. |
| Daria | CTO | Finishes the technical specification and its UML diagrams (task 2.0 – hospital); makes it read as a clean, professional document matching the required project template; sets the team's working policies. |
| Milko (you) | Project Manager | Breaks the plan into tasks with concrete time estimates so the project is ready by the deadline; owns the schedule below and unblocks the team. |
| Kolev & Panayot | Backend Developers | Build the Spring Boot API: REST controllers (api/), JPA models (domain/), repositories (repository/) and business services (service/), per the repo's source map. |
| Stanislav | Software / Architecture Engineer | Needs working knowledge across the stack (Java, TypeScript/Next.js, SQL); defines the overall MVC architecture and how the system fits together; owns the security/ layer and code-consistency reviews. |
| Iliyan & Valentin | Frontend Developers | Build the Next.js (App Router) + TypeScript UI – pages under frontend/app and screens/typed API client under frontend/src – for patients, doctors, rooms, procedures and the dashboard. |
| Anna | QA / Tester | Tests the application end-to-end: admission/transfer/discharge and procedure scenarios, roles & permissions, and the Playwright suite under frontend/e2e; verifies fixes. |
| Petar Dimitrov | Database Engineer | Owns the PostgreSQL schema and Flyway migrations (db/migration); designs the Patient, Doctor, Room, MedicalProcedure, Admission, PatientProcedure and User tables and keeps them in sync with the domain models. |

# 3. Role Notes

Leadership

- Ani (Team Leader) has final say on scope and represents the team externally.

- Milko, as PM, turns the plan into a time-boxed task list (see §5) and tracks it against the 25.09 deadline.

- Daria, as CTO, owns the technical specification itself: finishing its UML diagrams, formatting it to the official project template, and setting team working policies (branching, reviews, communication).

Engineering

- Backend (Kolev, Panayot): api/, domain/, repository/ and service/ layers in the Spring Boot app; enforces bed-capacity, uniqueness and referential-integrity rules.

- Frontend (Iliyan, Valentin): frontend/app and frontend/src – patient, doctor, room, procedure and dashboard screens, wired to the backend API.

- Stanislav (Software/Architecture Engineer) is the cross-stack reference: keeps the MVC split consistent between backend and frontend and owns the security/ (session, actor policy) layer.

- Petar Dimitrov owns the PostgreSQL schema and Flyway migrations feeding the domain models used by the backend team.

- Anna covers functional, role/permission and browser (Playwright, frontend/e2e) testing, and verifies that reported bugs are actually fixed.

# 4. Diagrams (minimum 8, distributed)

Per the team's requirement, at least eight diagrams must be produced and split across members so no one person is a bottleneck:

| Diagram | Owner | Location |
| --- | --- | --- |
| 1. E/R Diagram (data model) | Petar Dimitrov | docs/ |
| 2. UML Class Diagram | Daria | docs/ |
| 3. UML Use Case Diagram | Daria | docs/ |
| 4. Sequence Diagram – Admission flow | Kolev & Panayot | docs/ |
| 5. Sequence Diagram – Procedure recording | Kolev & Panayot | docs/ |
| 6. Component / MVC Architecture Diagram | Stanislav | docs/ |
| 7. Deployment Diagram (Next.js – Spring Boot – PostgreSQL, Docker) | Stanislav | docs/ |
| 8. Activity / User-flow Diagram (frontend) | Iliyan & Valentin | docs/ |

# 5. Documentation & Delivery Rules

- Architecture must be MVC end-to-end (enforced jointly by Stanislav and the backend/frontend leads).

- Both backend and frontend developers must contribute their own part of the code together with a short written explanation of what that part does – this feeds the docs/ folder (architecture, API, traceability, demo, verification).

- Daria finalizes the technical specification so the whole document reads as one consistent, professionally formatted piece, matching the official project template.

- Deadline for the full project, including diagrams and documentation: 25.09.

# 6. Collaboration & Tools

- Version control: Git, with a feature branch per module and review before merging to main (policy set by Daria).

- Task tracking: shared board covering the roster above, owned and updated by Milko.

- Communication: short recurring sync led by Milko to catch schedule slips early enough to still hit 25.09.

- Definition of done: implemented, tested (per Anna), reviewed (per Stanislav), and documented (per §5).

# 7. Day-by-Day Schedule (Fri 18 Sep – Fri 25 Sep)

The project week, broken down by day and by person, from kickoff to today's submission/defense:

| Day 1 – Fri, Sep 18 – Kickoff & Setup |  |
| --- | --- |
| Ani | Runs the kickoff; aligns scope with the assignment and confirms the week's goals. |
| Milko | Breaks the plan into daily tasks (this schedule) and sets up the tracking board. |
| Daria | Starts finishing the technical specification draft. |
| Stanislav | Sketches the overall MVC architecture skeleton. |
| Kolev & Panayot | Set up the Spring Boot project skeleton and the database connection. |
| Iliyan & Valentin | Set up the Next.js project skeleton and base routing. |
| Petar Dimitrov | Drafts the initial database schema. |
| Anna | Prepares the test plan and test-case list. |
| Day 2 – Sat, Sep 19 – Core Entities |  |
| Daria | Continues the spec; starts the UML Use Case diagram. |
| Stanislav | Reviews the architecture skeleton with the backend and frontend leads. |
| Kolev & Panayot | Implement the Patient entity, repository and controller. |
| Iliyan & Valentin | Build the patient list and add-patient form. |
| Petar Dimitrov | Finalizes the Patient/Doctor/Room tables; first Flyway migration. |
| Anna | Sets up the test environment and unit-test scaffolding. |
| Milko | Tracks Day 1–2 progress against the plan. |
| Ani | Checks in with the team; clears early blockers. |
| Day 3 – Sun, Sep 20 – Doctors & Rooms |  |
| Daria | Produces the UML Class diagram. |
| Kolev & Panayot | Implement the Doctor and Room entities/endpoints. |
| Iliyan & Valentin | Build the doctor and room screens. |
| Petar Dimitrov | Adds the Admission table migration. |
| Stanislav | Reviews the code so far for MVC compliance. |
| Anna | Writes unit tests for the patient module. |
| Milko | Mid-point status check against the schedule. |
| Ani | Reviews the documentation drafted so far. |
| Day 4 – Mon, Sep 21 – Admission & Discharge |  |
| Kolev & Panayot | Build the admission/discharge business logic (service layer). |
| Iliyan & Valentin | Build the admission/discharge forms and the dashboard skeleton. |
| Petar Dimitrov | Adds the MedicalProcedure and PatientProcedure tables. |
| Daria | Produces the Sequence diagram for the admission flow. |
| Stanislav | Designs the security layer (login/session handling). |
| Anna | Writes integration tests for the admission flow. |
| Milko | Flags any schedule risk to the team. |
| Ani | Runs a team sync; unblocks cross-role dependencies. |
| Day 5 – Tue, Sep 22 – Procedures & Reports |  |
| Kolev & Panayot | Build procedure recording and report/aggregation endpoints. |
| Iliyan & Valentin | Build the procedure screens and the patient detail page. |
| Petar Dimitrov | Adds data-integrity constraints and indexes. |
| Daria | Produces the Sequence diagram for procedure recording. |
| Stanislav | Reviews the deployment setup (Docker/Compose). |
| Anna | Tests role-based access control. |
| Milko | Updates the tracking board. |
| Ani | Starts outlining the defense/demo script. |
| Day 6 – Wed, Sep 23 – Integration & Bug Fixing |  |
| Kolev & Panayot | Fix backend bugs found during integration; finalize the API. |
| Iliyan & Valentin | Fix frontend bugs; polish the responsive layout. |
| Petar Dimitrov | Verifies the schema matches the final domain models. |
| Stanislav | Produces the Component/MVC architecture diagram; final code review pass. |
| Anna | Runs a full regression pass, including the Playwright e2e suite. |
| Daria | Finalizes spec formatting; supports the E/R diagram. |
| Milko | Confirms every diagram is on track for the deadline. |
| Ani | Reviews overall readiness. |
| Day 7 – Thu, Sep 24 – Documentation |  |
| Kolev, Panayot, Iliyan, Valentin | Write the per-module code explanations for the docs/ folder. |
| Petar Dimitrov | Finalizes the E/R diagram and database documentation. |
| Daria | Final proofread of the technical specification. |
| Stanislav | Final architecture/consistency check. |
| Anna | Runs final verification tests and signs off on quality. |
| Milko | Consolidates the final report. |
| Ani | Prepares the presentation for the defense. |
| Day 8 – Fri, Sep 25 (Today) – Submission & Defense |  |
| Ani | Leads the final review and the defense/demo. |
| Milko | Runs the final checklist and submits all deliverables. |
| Daria | Final proofread/formatting pass on the specification. |
| Stanislav | Final sanity check of the architecture before the demo. |
| Kolev & Panayot | Final smoke test of backend endpoints. |
| Iliyan & Valentin | Final smoke test of the UI; demo rehearsal. |
| Petar Dimitrov | Confirms the database is in the expected demo state. |
| Anna | Final smoke test before submission. |